Field Day 2022 – Planning Notes

As of: 6/13/22

Chairman: WA6E, Gerry
Co-Chair: KM6JBI, Herb

Next meeting: Thursday, June 16, 6:30 pm on zoom

Event: 25 and 26 June, Saturday and Sunday
Contest time: 1800 UTC Saturday until 1800 UTC Sunday
PDT: 11 a.m. Saturday until 11 a.m. Sunday
Setup: 24 June, Friday
Note: No setup before 5 pm on Thursday (Rule 3.3)
Operating Time Restrictions: If we set up before 11 a.m. Saturday, we can only operate for 24 hours
i.e. until 11 a.m. Sunday (Rule 3.2) Otherwise it goes until 2 pm on Sunday
NB: 2022 Rules can be downloaded at https://w6ek.groups.io/g/FD2022/files/

Suggested: Use computer for visitors/members to sign in

Where: Georgetown Airport

Important event reminders highlighted in green
Planning attention required highlighted in yellow

Operational Details:

1. Location
2. Antennas: AI6JB, Orion
3. Food: KQ6VP, Jim
4. Safety: KC6SLE, Greydon
5. Shelter:
6. Generators – Electrical Distribution
7. Radios
8. Network
9. Logging
10. Band Captain/Operations

Stations:
1. HF. Flex 6400M with tuner and 160-10m bpf (provided by AI6US)
2. HF. Icom IC7300 KD6HOF, Tim bringing complete station (w/ tuner) Secondary: FT8
3. HF. Yaesu FT10DX (provided by KM6RGO) (w/ tuner)
4. VHF and Higher
Anytone and antenna for 220 (AI6US)
Icom IC9700 for 2, 440 and 1.2ghz and 2m/70cm horizontal loop (AI6US)
Use radio for winlink messaging
KC6SLE knows the radio and Winlink?

5. Digital. Herb, KM6JBI (w/ tuner)
6. GOTA – 2m FM with a mast and dipole Thomas MJB will bring radio – Alan KB4GOJ has	beam antenna and mast.
Point beam west and leave it alone. VHF only to avoid HF interference
See special GOTA requirements under “9. Score Keeping”
Thomas KM6MJB and Jon, KI6RT will run station
Will use callsign KC6SLE

Classification: Class A. How many transmitters? GOTA, VHF and talk-in don't count. 4?
So Class 4A

    1. Talk-In / welcome table - WA8MPA will bring radio and antenna for this. 146.43 simplex (TAC 1)
      -Needs help for busy parts of day – perhaps EMS tent can help

Details:

1. Location

Georgetown Airport. It was used last year, had facilities and room to park RV’s. Without objection decision made by Chair.

Be sure to file our location with ARRL on their Field Day page - done

Need: hand towels and toilet tissue for bathrooms
Need to check this one week before the event - check with Scott or go see
Check with Scott about who will get key card – need somebody to be in charge

2. Antennas

-Chair: Orion, AI6JB
-Orion did the layout last year. Let’s just duplicate it.
What we did in 2021:
Orion hung antennas and brought feed line to each station
Each station “owner” sets up his own tent, table,

For 2022:
Map shows antennas and tent locations
 Antenna map located in files at https://w6ek.groups.io/g/FD2022/topics
Antennas we have:
Two 80M doublets
One hex beam 20m-6m and Pneumatic mast
AI6US and AI6JB (need truck with 2” receiver) Herb JBI will provide
One Triband beam and mast (N6ADT)
Paul – OHV – should pick up. Check with him
(need truck for ballast wheel mount)
Gary KN6AVC will provide – also has lumber rack to make platform for	working on antenna
40m/15m inverted V wire beam (AI6US)
Triplexer 20/15/10
160M Vertical antenna (30 to 40’ tall) – AI6JB (available but not bringing)
Only have one 10M filter (Jeff RGO has ordered a new one)
KC3PO provided 160m end fed long wire
     (need t-post and driver – Herb will bring)
Brian will bring GP95 and triplexer for 2, 440 and 1.2
Brian will bring 6 meter ground plane antenna
WU6X has Buckmaster 6 band OCF antenna he will bring – needs tuner	(Tim, HOF, will bring)
Will this be used? No.
This committee will provide feedline from each antenna to the appropriate station
Note comments in safety section on burying lines to avoid tripping hazard

3. Food

-Chair: Jim, KQ6VP, our cook emeritus

-Assistant:  Alan, KB4GOJ, 650-766-1934

-Friday night pizza (take up a collection from those eating)
Before event calculate a suggested price per slice
(Suggested $5 - $10 (2021 – spent $325)
        Club supplying water
Print out copy of their menu so people will know

-Sat night BBQ – food provided by club
Dinner will be BBQ Tri-Tip and Chicken
Side dishes provided by club
Ice cream: WB6LPJ will store in his motorhome

Tri-Tip – Recently $6.99/lb at Costco
    4 pounds yields 7 to 8 servings
Smart-n-final - $3.80/lb or $3.35 if you buy 50 lbs or more
Need 40 pounds of tri tip
Chicken

Side dishes (we will serve)
Cole Slaw – obtain from Smart N Final (don't forget dressing)
    1 gallon bottle of dressing should be enough
    20 pounds of cabbage for about 70 servings
Baked beans (provided by Jim)
Potato salad with red potatoes – Smart N Final
Ice Cream
2021 Scott kept it – 3 gallon size – vanilla, chocolate, strawberry
Bananas – Smart-n-final – Order in advance will hold for us
Chocolate syrup
Water
Milk and orange juice - Smart-n-final

Jim brings his own BBQ and utensils

-Breakfast last year was provided on Sat & Sun by AI6US
He served over 100 breakfasts
He has offered to do that again this year
Suggested Donation $5+

-What we did in 2021:
Club provided and served food – Saturday
Because of covid this was not a pot luck
Serving the food makes a better allocation per serving
Members were asked to pick food up and bring it to the site
Donation bowl at end of food line for $$$ contribution
Suggested donation for dinner was $10 and a sign was posted by $ bowl
Club will provide water
Club has coffee pots – Michael, K6ZUG, may have them
Brian will do RSVP list for dinner
Greydon has two ice chests he will bring with ice in them
Common table at dinner
Have people bring individual servings (bags) of snacks and drinks during the day
Saturday 2019 had 65 signed in for dinner
How many members can we expect to attend?
We will put up a poll before field day
        2021 Poll: 55 responses. 80% (about 44 people) wanted in-person event
Utensils, napkins
Greydon has two ice chests he will bring with ice in them
Brian ordered and prepaid the sides and ice cream from Smart N Final.

Peter WB6POT and his wife donated and picked up the banana split fixings in 2021.
Peter and Wayne W6DT picked up the prepaid ice cream and KN6MJB picked up the refrigerated side dishes.
Folks with the Class A RVs kept the salads and other refridge items.

Bring extra water hose to connect to bibs around the area.
Need people to bring ice chests with ice

4. Safety and Everything Else

- Chair: Greydon, KC6SLE

Safety Officer – We get extra 100 points for having a Safety Officer and having him/her certify to meeting FD Safety Rules.

Check-In/Talk-In table – First Aid Tent will be combined with the check-in/talk-in table.
Club brochures? ARRL brochures? Sign-in sheet?  CR Code on sign

Need site lighting. Who provides? AC or DC? RF interference?
Each station brings what they need
Send everybody a notice of this and what they need to bring.

Print the W6EK FD exchange sign to post at each station.
… and a checklist for logging
Name of operator, mode, band, time – make note of this in log
Smitty will make some band charts and laminate them

Designate somebody as contact for parking/camping information
Talk to MPA

Post signs at east side airport access gates with call- in frequency and a map how to access the campground. Herb will do.

Several people suggested last year to place BIG arrows pointing left inside the main gate directing folks down the West side airport access road to the campground. The signs posted at the gate on the chain link fence were not adequate. Herb

Hand sanitizers and wipes at each station, welcome table, food area

Check on bathroom supplies (soap, tp and tri-fold hand towels), bath and shower doors unlocked and hot water tank turned on.

Check that water is turned on and hoses at bibs and run clear for a few minutes.

Check with Terry's Pizza (530) 333-1213 a week or more before event to verify advance notice procedure for placing a large order. Verify the online pizza menu and prices. https://terryspizzeriagrill.food94.com/

What we did in 2021 (some of which became moot when KK6AIR provided generator)
-- Put Caution tape around the immediate generator area to keep it free and clear of people and foot traffic. No Smoking signs for this area.
-- At least one appropriate sized fire extinguisher in Generator area.
-- Fuel Storage:
2022: KK7AIR Generator – No Refill or fuel storage will be on the site
2021: Pretty much the same as the Generator area, Designated area clear of trees and vegetation. Suggest using tall red cones and Caution tape to keep people and traffic out. No Smoking signs.  I’ll handle this if you agree.
Fuel storage should be a reasonable distance from the generators, not stored with the generators.
Plan on at least one appropriate sized fire extinguisher located within fuel storage area.
Refueling:  Generators should not be refueled while running, should be allow to cool off for a few minutes before refueling.  If we locate the two units a few feet apart we can probably take one off line at a time to fuel. May have to have several stations stand down for a short period while we do this, maybe not, depends on load.  Figure generators are going to need to be topped of at least every six hours.
First Safety: No significant failures or issues here in 2021.  We met and exceeded all ARRL safety requirements, even added many others.

What we plan to do in 2022:
--Place caution tape around antenna guys, ground stakes and feed lines
KC6SLE will provide and set up on Friday
--Fire extinguisher at bbq, cook table, generator area. KC6SLE to provide
--Last year Thomas and Greydon found the best way to eliminate power and antenna cord tripping hazards was to bury such a few inches below the surface.  This year we will bring the appropriate digging tools to make this a much easier  and quicker task.
--We will also provide a list of local area first responders, and contact information for such, should an incident occur that needs advanced medical response and transport.
Scott said we can use his water truck – dust control and fire suppression
Bring some garden hoses

First Aid Tent:
Thomas, KM6MJB will coordinate this
Locate tent closer to an operational tent
Need to have more than just one person on our medical team.
Names suggested: W6EMS
Volunteers: KM6RGO, KD7G, K6SAL
Need to be at the tent or near it
First Aid tent will have signage, be clearly identified
K6SAL will bring AED machine

5. Shelter

- Chair: Don, WB6LPJ

Requirement: Six 10x10 and two 10x20

2021
2021: Brian has one10 x 10 pop up
2021: Chip has 3 pop ups
2021: Tim, KD6HOF, as one
2021: Al has 10 by 10 in his rv
2021: Orion has an 8x8
2021: Don, WB6LPJ, has two 10x10 pop-ups

2022: Our requirement: One per station minimum plus EMS and welcome tents = 10
Club has two 10 x 20 – used in food area*
Brian, AI6US, has one 10x10*
WA8MPA, Jim, has two 10x10*
WB6LPJ, Don, has one 10x10*
KI6LOP, Russ, has one 10x 10
KD6HOF, Tim, has one 10x 10*
KN6MJB has 10x10 and a table
KM6RGO has 10x10*
* Available on Friday
Two 8 foot tables and 8 chairs for VE
Note: Scott has tables at his hangar for this.

Don will need help setting up on Friday

-Comment from 2021: CW station needs to be near outskirts so it is quieter
-Bring tables

6. Generators - Electrical

- Chair: ___________
-Scott, KK6AIR, has offered the use of his 45 kw generator and dist boxes
2021 – Generator used 6 gallons of diesel fuel in 48 hours

-What we did in 2021
Orion headed this effort
Al, N6ADT, has 2k Honda w/ extended run
Est max total load would be 4 to 5 kw
Orion, AI6JB, as the interface cable for two generators
Greydon, KC6SLE, as a 2ki and gas cans
We only used Scott, KK7AIR’s generator
- Jon, KI6RT, had solar panels and controller in 2021
WA8MPA has the heavy duty power distribution gear we have used in the past.
Scott, KK7AIR provided distribution from the generator (parked next to restrooms) down to camp.

2022: Bring generators for standby. Who will bring them:
KM6RGO – 2200i
AI6JB – has another 2200i and a “parallel cable” to join the two generators
N.B.: only certain models can parallel with a 2200i

7. RF Generators (i.e. Radios)

- Chair: ______________

- Traditionally we have 5 stations
- GOTA station? We had one 2m GOTA in 2021 GOTA – 2m FM with a mast and dipole
- Amir, N6ADL, set up a VHF station in 2021 (will not be here this year)
- Tim, KD6HOF, bringing complete station (tuner)
- Brian, AI6US, will bring his Flex 6400M with tuner and 160m – 10m BPF
- Jeff, KM6RGO, will bring his FT10DX (with tuner)
- Brian will bring his Anytone and antenna for 220
- Herb, KM6JBI, will set up a primary digital station (tuner)
- Bring gear to support 2nd digital (flexible mode) station KD6HOF will bring it

- Operators were advised to bring their own headphones
-Comment from 2021: CW table needs to be near outskirts so it is quieter for ops

-Satellite – 100 bonus points for at least one QSO via satellite.
Our sat guys at Western States K6BAA and KO6TH
AI6US offering to bring IC-9700 for satellite station
FM contacts difficult – SSB better
Only one bonus no matter how many QSO's made via satellite
Interest in doing this is nonexistant. Don't bother.

Feedline – N6ADT and AI6US

8. Networking

-Chair: WA8MPA, Jim
Co-Chair: WU6X - Dennis

This year we will use rf networking – not cable
Club has the logging computers – WA8MPA has possession of them
Update: Club has 9 laptops. All updated as of Apr 2022. Has latest N3FJP software
All network very well.
Closed network – only available to pre-provisioned computers
To eliminate potential conflicts in system
Will do the ft8 computers manually using club computers will require an operator and logger at each ft8 station just like every other station.
Issue: Heat in afternoon. MPA bought one laptop fan cooler on which laptops can sit.
Cost about $30. USB powered Tested – works great. No RFI
Ordered 5 more

Bring power bricks if available to avoid EMF noise from power supplies

9. Score Keeping

  - Chair: Dennis WU6X
-What we did in 2021
-Jim, WA8MPA, set up the system for logging
-AI6US submitted score in 2021
Total score: Bonus 1650 1290 qso 2580 total score
We were able to include at-home participant scores, Aggregate Club Score now Permanent	rule with ARRL Field Day
Had Zoom 24/7 in 2021, but only two viewers
-Can we have a central monitor to show real-time scores? Jim, WA8MPA has set-up scoring	monitor and string map in past years.

- Suggestion from 2021:
-Harden network to avoid EMP interference
-Have a logger at each station is a plus.
-People coming up to talk is distracting but unavoidable
-Keep a manual log at the digital station – makes a team not just one guy.
-If a second FT8 station – call CQ only – other station will know if dup

Review ARRL rule changes for 2022

GOTA Station special rules: The single control operator (operating under their personal call sign) needs to understand the GOTA rules, prepare and manage the log sheets (not logged into the main W6EK software), collect the GOTA operators information (name / age / minimum number of contacts per GOTA operator (10) / award GOTA pins), coordinate band usage with the VHF station lead.

Messages: Who will take on this responsibility? KC6SLE

Rule 7.3.5 – 100 points for originating message to ARRL Section Manager (KP4MD) You should include the club name, number of participants, Field Day location, and number of ARES operators involved with your station. The message must be transmitted during the Field Day period and a copy of it must be included in your submission in standard ARRL radiogram or no credit will be given. The message must leave or enter the Field Day operation via amateur radio RF.

Rule 7.2.6 - Message Handling: 10 points for each formal message originated, relayed or received and delivered during the Field Day period, up to a maximum of 100 points (ten messages). Copies of each message must be included with the Field Day report. The message to the ARRL SM or SEC under Rule 7.3.5. does not count towards the total of 10 for this bonus.

Rule 7.3.9. W1AW Bulletin: cial 100 bonus points for copying the speField Day bulletin transmitted by W1AW (or K6KPH) during its operating schedule during the Field Day weekend (listed in this rules announcement). An accurate copy of the message is required to be included in your Field Day submission. (Note: The Field Day bulletin must be copied via amateur radio. It will not be included in Internet bulletins sent out from Headquarters and will not be posted to Internet BBS sites.)

ARRL Field Day Bulletin Schedule Attached Below

Need battery for battery-only contacts for extra points. Jeff will bring.

Important: Copy the ARRL Bulletin on Friday to get that chore out of the way. Have it copoied by as many stations as possible so as to make sure it is copied correctly.

Use one station at the start to make five QSO's using battery only for extra points. Perhaps VHF.

Rule 7.3.8. Alternate Power: 100 bonus points for Field Day groups making a minimum of five QSOs without using power from commercial mains or petroleum driven generator.

10. Band Captain/Operations

- Chair: Herb, KM6JBI
-What does band captain do? Monitors the bands looking for most activity and also makes sure we aren’t wasting time on bands that have died. Assigns band assignments to various stations to prevent interference.
-Is in charge of handing out band filters
SFARC has 20/15/10m triplexer,
SFARC Bandpass Filters: 1x-160m, 2x- 80m, 2x-40m, 2x-15m, 1x-10m (AI6US has 1x-6m	BPF) Orion has them
RGO Ordered one more for 10 meters. Brand: Dunestar 300-28 for 10 meters.

Operations – schedule operators at various stations.
Create a staffing plan. This will ensure stations are manned at all times with no gaps.
WU6X – Dennis – says he will man the CW station
Previous CW ops: Peter, WB6POT, Wayne, W6DT. Maybe Earl, W6GPB, and Derick,	W6DER
Call-in frequency: 146.43 TAC 1 (Club repeater will be busy with Western States event)

Print a band plan for each station.

Provide a notebook and pens for each station KM6RGO ordered from Amazon

11. Other

VE Testing

2 pm on Saturday
$14 cash or check
Candidate needs FRN in advance
Scott, KK7AIR, offered his hangar for testing
CVE is K6BSY – wants 2 tables and 8 chairs
Hangar has tables – need chairs
VE: AI6US;
Mention this in PR

T-shirt.
Complete.
Can order online: https://www.customink.com/g/wun0-00ck-rssh
Guaranteed 25 Order totaled 42 shirts in 2022
Pay for shirt when ordered on line.
In 2019 club ordered 25 ARRL T-shirts
In 2019 club ordered 30 ARRL pins (2021 Ordered 20 ARRL Pins – suggest to order	GOTA pins this year) 2021 had 8 GOTA operators Pins don't change year to year
KM6RGO will order pins
Cost is about $21 this year for our tshirts

Pins: Gave some away for GOTA operators and others. Budget and order.

Education: For extra points have a presentation on something for purposes of “education.” Greydon will make a presentation on fox hunting to satisfy this requirement.
Bring club PA system Pick up after June club meeting

Publicity: Smitty, WB1G, has agreed to do publicity
-Remember VE testing
Need a photographer/videographer – everybody take pictures

Comments from 2021:
Need more signage on how to access the place.
164 people visited the site in 2021
There did not seem to be any attempt to have people sign up for stations and times prior to the event in an effort to keep stations occupied (band conditions may have influenced this as well).  Perhaps a staffing plan would be beneficial in the future.
The logging system shutdown numerous times during the day which put all stations on hold.  Think everyone is well aware of this and sure planning is already underway to address this.

Jim, WA8MPA, needs help transporting all the stuff up to the FD site.
Alan et al

SHOPPING LIST 2022

Foil Serving Pans - 8x half / 4x Full - Smart n Final
Coffee – club has none – Jim will buy it
Salt / Pepper Shakers 6 ct - Smart n Final
Coleslaw - $7.99 per container Buy 6
Smart n Final – 48 oz 7.99 / 13 3.5 oz servings per container
Brand: First Street
Product Code: 00041512110832
https://www.smartandfinal.com/shop/product/first-street-classic-coleslaw/641934
Note: Make sure it comes with dressing

Red Potato Salad - $10.29 per container Buy 5
Smart n Final – 5 lbs (80 oz) / 16 x 5 oz servings per container
Brand: First Street
Product Code: 00041512163449
https://www.smartandfinal.com/shop/product/first-street-red-skin-potato-salad-with-herbs/688126

Sweet Hawaiian Rolls - $5 per bag Buy 7
Smart n Final – 24 count / 12 servings per bag
Brand: First Street
Product Code: 00041512173264
https://www.smartandfinal.com/shop/product/first-street-sweet-rolls-hawaiian/2221089

Ice Cream - (Special Price - 3 for $68.97)
Smart n Final – 3x 3 lbs
Buy 1 of each

Vanilla $25.99 each
Brand: First Street
Product Code: 00041512099076
https://www.smartandfinal.com/shop/product/first-street-ice-cream-premium-vanilla/675670

Chocolate $25.99 each
Brand: First Street
Product Code: 00041512099052
https://www.smartandfinal.com/shop/product/first-street-ice-cream-premium-chocolate/662517

Strawberry $25.99 each
Brand: First Street
Product Code: 00041512099014
https://www.smartandfinal.com/shop/product/first-street-ice-cream-premium-strawberry/677096

Reddi Whip - $4.99 each Buy 3
Smart n Final 3x
Brand: Reddi Wip
Product Code: 00070272481043
https://www.smartandfinal.com/shop/product/reddi-wip-original-whipped-light-cream/675125

Hershey's Chocolate Syrup - $4.99 each
Smart n Final 2x 48 oz Buy 2
Brand: Hershey's

Product Code: 00034000000470
https://www.smartandfinal.com/shop/product/hersheys-genuine-chocolate-flavor-syrup/650008

Hershey's Caramel Syrup
Smart n Final 3x 22 oz at $2.60 each Buy 3
Brand: Hershey's
Product Code: 00034000003662
https://www.smartandfinal.com/shop/product/hersheys-indulgent-caramel-flavor-syrup/646665

Bananas
Smart n Final - 24x at .69 per lb Buy 24
Product Code: 00204011000008
https://www.smartandfinal.com/shop/product/bananas-each/617650

Diced Walnuts $4.99 per bag This does NOT include peanuts.
Smart n Final 2x bags
Brand: Diamond
Product Code: 00076811820021
https://www.smartandfinal.com/shop/product/diamond-milk-chocolate-chip-walnut-baking-mix-ins/2273942

Water - $4.49 KM6RGO will buy this at Costco
Smart n Final 10 cases of 35
Brand: First Street
Product Code: 00041512152542
https://www.smartandfinal.com/shop/product/first-street-water-purified-drinking-35-bottle-value-pack/613416

Dinner Plates - Heavy Duty – 75 to 100

Soup Bowls for beans and Banana Splits – get 200 or so

Paper Cups for Orange Juice - 9 oz 200ct

Garbage bag liners – 30 gallons – get 20 or 30

2022 W1AW FIELD DAY BULLETIN SCHEDULE

Mode	Pacific Time	UTC

FRIDAY
CW	5:00 PM	0000 (Sat)
Digital	6:00 PM	0100
Phone	6:45 PM	0145
CW	8:00 PM	0300

SATURDAY
CW	7:00 AM	1400
Phone	8:00 AM	1500
CW	5:00 PM	0000 (Sun)
Digital	6:00 PM	0100
Phone	6:45 PM	0145

SUNDAY
CW	7:00 AM	1400
Phone	8:00 AM	1500
Digital	9:00 AM	1600

K6KPH Field Day Bulletin Schedule

SATURDAY
CW	7:30 AM	1430
CW	5:30 PM	0030 (Sun)
Digital	6:30 PM	0130

SUNDAY
CW	7:30 AM	1430
Digital	9:30 AM	1630

W1AW will operate on the regularly published frequencies.

CW frequencies are 1.8025, 3.5815, 7.0475, 14.0475, 18.0975, 21.0675, 28.0675,
50.350 and 147.555 MHz.

Digital frequencies are 3597.5, 7.095, 14.095, 18.1025, 21.095, 28.095, 50.350
and 147.555 MHz. (Note: W1AW will transmit the Field Day Bulletin using 45.45
baud baudot, PSK31 {BPSK Mode}, and MFSK16 in this mode order).

Phone frequencies are 1.855, 3.990, 7.290, 14.290, 18.160, 21.390, 28.590,
50.350 and 147.555 MHz.

---------------------------------------------------------------------------

The Maritime Radio Historical Society's station K6KPH will transmit the "W1AW"
Field Day message for the benefit of West Coast stations on 3.5815, 7.0475,
14.0475, 18.0975 and 21.0675 MHz. The frequencies for K6KPH Teleprinter (RTTY,
PSK31 and MFSK16) will be 7.095 and 14.095 MHz (in this mode order).

At the time of publishing this packet but be sure to check the ARRL Main News
page (www.arrl.org) if case of any last-minute changes.

Revised: 3/2022